Term Project

Centralized Computing Service for Business

By LingxuanYe

ye.linx@northeastern.edu

Submission Date: January 22, 2023

EMGT5220: Engineering Project Management, Spring 2023

Northeastern University

Instructor: Prof. George Kontopidis

Table of Contents

1.	Purpose	3

2.	Objective	3

3.	Scope	3

4.	Funder/Investor	3

5.	Critical Success Factors	3

6.	Assumptions	3

7.	Technical Approach	3

8.	Organization	3

9.	Project Plan	3

a.	Work Breakdown Structure (WBS)	3

b.	Resource Plan and Responsibilities (RACI)	3

c.	Financial Plan	3

d.	PERT Chart <choose a Tool as we discussed in the class>	3

e.	Gantt Chart <add and balance resources>	3

10.	Risk Assessment (SWOT, FMEA, RPN)	3

11.	Monitoring and Control	3

12.	Summary	3

13.	Appendix	3

a.	MindMap	3

b.	Tool#1 <choose a Tool as we discussed in the class>	3

c.	Tool#2 <choose a Tool as we discussed in the class>	3

14.	References	3

Revision History <required for all Draft submissions. Not required for the final Project Report>

| 01/22/2023 | Draft #1: Finish proposal, manage a plaintext version with git |
| --- | --- |
| 02/12/2023 | Draft #2: Technical Approach; Organization; WBS; Financial Plan |
| etc |  |

Purpose

Computers are of great importance to all business companies. However, to those companies that are not in Information Technology industry, managing and maintaining office computer cluster is way harder than expected: because those computing devices are distributed to employees, the hardware/software maintenance is not guaranteed. Due to the sophisticated nature of computer and the ignorance of mass majority, office computers are frequently facing virus infections, business secret leaks, runtime environment conflicts, crashing and all other unexpected troubles. In fact, almost all companies have to set up a whole IT department with great cost to handle those problems, if and only if the problem is perceived by the user. This project mainly aims to provide a centralized computing service in order to reduce the occurrence of problems mentioned above and lower the cost of operations and maintenance.

Objective

The main objective of this project is to set up a centralized server locally with terminals distributed to every employees' office instead of distributing computers. Users (employees) can no longer get access to the hardware and their behaviors to the operating system are limited. Administrator can preinstall a list software for business purpose and other software that user wishes to use can only run in a sandbox. This project also provides a series of supporting services. The project aims to serve all companies especially those with no intersection with information technology.

Scope

The scope of the project is to provide a whole set of services including installation, operating system image procurement, virtual machine customization and distribution, operations engineering training and technical support.

Funder/Investor

The investor for this project will be an angel investor looking to make a seed investment in company operation services. Since this project is relatively small scale and low-end, in the later stages of the project development, it is less likely to require to be funded. The whole funding lifecycle should end right after the demo being released. The end user of this project are the company owners who wish to reform the workflow of the company business for a better information security.

The companies will pay an upfront fee for the whole set of installation and a annual fee for technical support. It also requires to hire operations engineers of our project's own. In the later stages, a partnership will be formed with some educational institutions that will help training operations engineers from the company's IT department. The upfront fee should cover the hardware/software procurement fee, installation fee, our project's overhead and earning. The dividend of the investor will be paid for 5 years and after which all the equity will be repurchased.

For the end-users, their IT departments will no longer need to employ people interfacing with other departments. After the separation of computer using and maintaining, the departments inside the company are no longer high coupling, which dramatically reduces the communication cost.

Critical Success Factors

Assumptions

<Critical Success Factors and Assumptions should be filled after Draft#2 AFTER completing Risk Assessment. Do not fill this in early>

Technical Approach

The technical approach of this project will include the following modules.

  - Installation

This module includes server host machine installation, cable installation, Input/Output devices (including mouse, keyboard, camera, microphone, monitor, etc.) integration. Those I/O devices are regarded as the user terminals.

  - Operating system configuring

Customize the operating system configuration in order to satisfy the company's own needs and make image of the operating system.

  - Virtual machine deployment

Instantiate virtual machines for every employees from the highly customized image. Every employee should be assigned an individual virtual machine for work.

  - Maintenance

Monitor virtual machines' status and fix problems in time. Backup user documents periodically in case people make their machines crash.

Organization

The organizational structure for this project will be a weak matrix structure. This structure combines functional and projectized structures to balance both the efficiency of functional specialists and the focus of the project team.

Project Manager: The Project Manager will be responsible for overall project planning, execution, and closing. They will oversee the project team and report directly to the executive sponsor.

Technical Lead: The Technical Lead will be responsible for technical aspects of the project, including software procurement, configuration, and deployment. They will work closely with the Project Manager and provide technical guidance to the project team.

Operations Engineer: Operations Engineers will be responsible for the day-to-day maintenance and management of the centralized server and terminals. They will also provide technical support to end-users and work with the Technical Lead to resolve any technical issues.

Financial Manager: The Financial Manager will be responsible for budgeting, financial tracking, and financial reporting for the project. They will work closely with the Project Manager to ensure the project stays within budget and is financially feasible.

Marketing Manager: The Marketing Manager will be responsible for promoting the project to potential end-users and investors. They will work closely with the Project Manager and Financial Manager to develop a marketing strategy and build a brand for the project.

In addition to these core team members, the project may also require the involvement of external consultants, contractors, and vendors. These individuals will work closely with the project team to provide specialized expertise and support as needed.

Overall, the weak matrix structure will allow for a balanced approach that effectively leverages both the expertise of functional specialists and the focus of the project team. By combining the strengths of functional and projectized structures, the project is more likely to achieve its objectives in a timely, efficient, and effective manner.

Project Plan

Work Breakdown Structure (WBS)

The table represents a Work Breakdown Structure (WBS) for a project:

Table 1. WBS

| ID | Task | Responsibility | Duration (days) | Preceding Task |
| --- | --- | --- | --- | --- |
| 1 | Project Initiation | Project Manager | 5 | N/A |
| 2 | Identifying the project requirements and objectives | Project Manager | 2 | 1 |
| 3 | Defining the project scope and constraints | Project Manager | 2 | 2 |
| 4 | Assessing the project feasibility | Project Manager | 2 | 3 |
| 5 | Identifying the stakeholders and securing their involvement | Project Manager | 2 | 4 |
| 6 | Developing the project charter | Project Manager | 1 | 5 |
| 7 | Planning and Preparation | Project Manager | 5 | 6 |
| 8 | Developing the project schedule | Project Manager | 3 | 7 |
| 9 | Developing the project budget | Project Manager | 2 | 7 |
| 10 | Developing the risk management plan | Project Manager | 2 | 7 |
| 11 | Developing the quality management plan | Project Manager | 2 | 7 |
| 12 | Developing the communication plan | Project Manager | 2 | 7 |
| 13 | Server and Terminal Installation | Project Manager | 7 | 12 |
| 14 | Procuring the hardware and software components | Project Manager | 2 | 13 |
| 15 | Installing the server host machine | Technical Lead | 2 | 14 |
| 16 | Installing the input/output devices (terminals) | Technical Lead | 2 | 15 |
| 17 | Integrating the terminals with the server host | Technical Lead | 2 | 16 |
| 18 | Testing the server and terminal installation | Technical Lead | 2 | 17 |
| 19 | Operating System Configuration | Project Manager | 5 | 18 |
| 20 | Customizing the operating system to meet the company's requirements | Technical Lead | 2 | 19 |
| 21 | Creating an image of the operating system | Technical Lead | 2 | 20 |
| 22 | Virtual Machine Deployment | Project Manager | 5 | 21 |
| 23 | Instantiating virtual machines for each employee | Technical Lead | 2 | 22 |
| 24 | Configuring the virtual machines to meet the company's requirements | Technical Lead | 2 | 23 |
| 25 | Deploying the virtual machines to the employees | Technical Lead | 2 | 24 |
| 26 | Testing the virtual machine deployment | Technical Lead | 2 | 25 |
| 27 | Monitoring the virtual machines for any issues | Technical Lead | N/A | 26 |
| 28 | Providing technical support to end-users | Technical Lead | N/A | 26 |
| 29 | Backing up user documents | Technical Lead | N/A | 26 |
| 30 | Fixing any issues with the virtual machines in a timely manner | Technical Lead | N/A | 26 |

Resource Plan and Responsibilities (RACI)

Table 2. RACI

| WBS ID | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| 1 | Project Manager | Project Manager | N/A | N/A |
| 2 | Project Manager | Project Manager | N/A | N/A |
| 3 | Project Manager | Project Manager | N/A | N/A |
| 4 | Project Manager | Project Manager | N/A | N/A |
| 5 | Project Manager | Project Manager | N/A | N/A |
| 6 | Project Manager | Project Manager | N/A | N/A |
| 7 | Project Manager | Project Manager | N/A | N/A |
| 8 | Project Manager | Project Manager | N/A | N/A |
| 9 | Project Manager | Project Manager | N/A | N/A |
| 10 | Project Manager | Project Manager | N/A | N/A |
| 11 | Project Manager | Project Manager | N/A | N/A |
| 12 | Project Manager | Project Manager | N/A | N/A |
| 13 | Project Manager | Project Manager | Technical Lead | N/A |
| 14 | Project Manager | Project Manager | Technical Lead | N/A |
| 15 | Technical Lead | Technical Lead | N/A | Project Manager |
| 16 | Technical Lead | Technical Lead | N/A | Project Manager |
| 17 | Technical Lead | Technical Lead | N/A | Project Manager |
| 18 | Technical Lead | Technical Lead | N/A | Project Manager |
| 19 | Project Manager | Project Manager | Technical Lead | N/A |
| 20 | Technical Lead | Technical Lead | N/A | Project Manager |
| 21 | Technical Lead | Technical Lead | N/A | Project Manager |
| 22 | Project Manager | Project Manager | Technical Lead | N/A |
| 23 | Technical Lead | Technical Lead | N/A | Project Manager |
| 24 | Technical Lead | Technical Lead | N/A | Project Manager |
| 25 | Technical Lead | Technical Lead | N/A | Project Manager |
| 26 | Technical Lead | Technical Lead | N/A | Project Manager |
| 27 | Technical Lead | Technical Lead | N/A | Project Manager |
| 28 | Technical Lead | Technical Lead | N/A | Project Manager |
| 29 | Technical Lead | Technical Lead | N/A | Project Manager |
| 30 | Technical Lead | Technical Lead | N/A | Project Manager |

Financial Plan

Table 3. Monthly Projectized Budget

| Month | Equipment/Hardware Procurement | Installation | Operating System Configuring | Virtual Machine Deployment | Maintenance | Marketing | Overhead | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | $10,000 | $15,000 | $5,000 | $10,000 | $3,000 | $2,000 | $2,000 | $47,000 |
| 2 | $0 | $0 | $0 | $0 | $3,000 | $2,000 | $2,000 | $7,000 |
| 3 | $0 | $0 | $0 | $0 | $3,000 | $2,000 | $2,000 | $7,000 |
| 4 | $0 | $0 | $0 | $0 | $3,000 | $2,000 | $2,000 | $7,000 |
| 5 | $0 | $0 | $0 | $0 | $3,000 | $2,000 | $2,000 | $7,000 |
| 6 | $0 | $0 | $0 | $0 | $3,000 | $2,000 | $2,000 | $7,000 |
| 7 | $0 | $0 | $0 | $0 | $3,000 | $2,000 | $2,000 | $7,000 |
| 8 | $0 | $0 | $0 | $0 | $3,000 | $2,000 | $2,000 | $7,000 |
| 9 | $0 | $0 | $0 | $0 | $3,000 | $2,000 | $2,000 | $7,000 |
| 10 | $0 | $0 | $0 | $0 | $3,000 | $2,000 | $2,000 | $7,000 |
| 11 | $0 | $0 | $0 | $0 | $3,000 | $2,000 | $2,000 | $7,000 |
| 12 | $0 | $0 | $0 | $0 | $3,000 | $2,000 | $2,000 | $7,000 |
| Total | $10,000 | $15,000 | $5,000 | $10,000 | $36,000 | $24,000 | $24,000 | $119,000 |

PERT Chart <choose a Tool as we discussed in the class>

Gantt Chart <add and balance resources>

Risk Assessment

<must include the following subsections SWOT, FMEA, RPN, Mitigation plan>

Monitoring and Control

Summary

Appendix

- MindMap

- Tool#1 <choose a Tool as we discussed in the class>

- Tool#2 <choose a Tool as we discussed in the class>

References

Do not forget:

- Start working in a section only after we cover the related material in the class.

- Brackets <> are meant to show what to write. Remove them from everywhere.

- Each section must have a couple of sentences as an introduction

- Captions are required in all Tables and Figures!!!